BOROUGH OF ALPHA

GENERAL CAPITAL PROJECTS AND WATER UTILITY

ENGINEERING STATUS REPORT

February 11, 2020

PREPARED BY:

REMINGTON & VERNICK ENGINEERS

232 KINGS HIGHWAY EAST

HADDONFIELD, NEW JERSEY 08033

(856) 795-9595

www.rve.com

ACTION ITEMS

None

ROADWAY AND GENERAL ENGINEERING PROJECTS

- Homa Lane Drainage Improvements

ESTIMATED COMPLETION OF DESIGN:  To Be Determined

ESTIMATED COMPLETION OF CONSTRUCTION: To Be Determined

ESTIMATED CONSTRUCTION COST:  $250,000

CONTRACTOR: To Be Determined

Field survey including the wetlands delineation is complete. Base plans are complete and we began the hydraulic modeling.  A NJDEP pre-application meeting was held on September 26, 2016. Hydraulic design and the plans are complete. The Borough needs to provide the certified property owner list within 200 feet of the project for notification under the NJDEP application requirement. A draft Phase IA study has been completed and will be submitted with the NJDEP application. The Phase IA is recommending a Phase IB but the NJDEP will make that determination. The plans and NJDEP application is complete. The certified property owner list has been completed and sent to our office. The NJDEP applications were submitted to the NJDEP on January 25, 2017. We received comments from the NJDEP on our submitted application and we are addressing the comments. Mitigation requirements are being reviewed by the NJDEP. A meeting occurred with the NJDEP for May 3, 2017 NJDEP to discuss the mitigation.  The NJDEP new rule changes will allow the culverts to be replaced under Homa Lane assuming it can be proven Homa Lane overtops during small rain events. This will be a less expensive option for the Borough but will need permission from the Homa’s to replace the culvert. Discussion with the Homa’s need to occur to determine if permission will be granted to replace the culvert. A letter was received from The NJDEP and a response was sent from our office requesting the application remain active. A meeting was held with Ken Homa, property owner and they are willing to give an easement to the Borough for the replacement of the pipe at Homa Lane. Council authorized the preliminary engineering phase of the project at their October 22, 2019 Council Meeting. Survey and base have been completed.  Hydraulic analysis has continued, and results should be completed by the end of February 2020.

- IndusTRIAL DRIVE/EDGE ROAD Connector road

ESTIMATED COMPLETION OF DESIGN:  December 2018

ESTIMATED COMPLETION OF CONSTRUCTION: October 2019

CONSTRUCTION COST:  $505,194.46

CONTRACTOR: Top Line Construction

We were authorized for the engineering services by Council at the November 13, 2017 Council Meeting. A preliminary layout was prepared and we met with the adjacent property owners to discuss and it was agreed by all a 70 foot ROW will be established. Meets and bounds descriptions are being prepared for the dedication to the Borough. We met with Hunterdon Transformer to review the plans and discuss various issues effecting their property ROW is being secured through deeds of dedication by the Borough Attorney. Council authorized RVE to advertise the project for Public Construction Bids at the February 19, 2019 Council Meeting. Warren County SCD application was submitted for approval to the Soil Conservation district.  Council awarded a construction contract to Top Line Construction at their April 23, 2019 meeting in the amount of $505,194.46. A pre-construction meeting was held on May 16, 2019 and the notice to proceed was given on May 20, 2019. Remaining work will be completed upon substantial construction of adjacent warehouse development. A temporary asphalt curb was installed to deter erosion prior to the development of the adjacent property. Construction will be completed in the Spring of 2020 since the adjacent development has not constructed their storm sewer system which impacts the completion of the Borough’s contract.

- 2019 Road Program (North BoulEvard Phase III and South Boulevard)

ESTIMATED COMPLETION OF DESIGN:  May 2019

ESTIMATED COMPLETION OF CONSTRUCTION: May 2020

CONSTRUCTION COST:  $658,524.75

CONTRACTOR: Capitol Paving and Contracting

Borough Council authorized the engineering services at their February 19, 2019 Council Meeting. Final documents are complete and they have been submitted to the NJDOT for review and comment prior to being advertised for construction bids. The NJDOT has finalized the grant agreement and placed into their system. Documents submitted to the NJDOT have been reviewed and approved. The Project has been advertised for construction bids and bids were received on August 13, 2019. The bids exceeded the engineers estimate and Borough’s budget. The low bidder has agreed in writing to hold their bid for Council to bond for the money and make a construction contract award in January 2020.  Council Awarded the construction contract to Capitol Paving at their January 14, 2020 meeting, Contracts have been prepared and executed by the contractor. They have been submitted to the Borough for full execution. Construction is anticipated to begin near the end of March 2020.

- Municpal Pool Demolition

ESTIMATED COMPLETION OF DESIGN:  March 2019

ESTIMATED COMPLETION OF CONSTRUCTION: March 2020

CONSTRUCTION COST:  $78,599.00

CONTRACTOR: CMS Services

Borough Council authorized the engineering services at their February 19, 2019 Council Meeting. Construction documents are complete and the project was advertised for construction bids. Bids were received and there was a three way tie for the low bid of $55,000. Project was re-advertised with changes to the scope of work as directed and one acceptable bid was received at $128,000. Council rejected the bids and a meeting was held with prier bidders to discuss submission of a best and final price. The prices were be submitted to Sean Canning on Monday July 8, 2019 at 10 AM and CMS Services, LLC were the low bid submitted at $78,599.00. Council awarded the construction contract at their October 7, 2019 Council Meeting. A preconstruction Meeting was held on October 31, 2019.  Contracts have been prepared and executed by the contractor and are with the Borough for full execution. Contracts have been fully executed and returned to all parties. The Notice to Proceed was issued for February 10, 2020. The contractor anticipates beginning the work at the end of February 2020.

- 2020 Road Program (5th Avvenue Phase II and East Central Avenue)

ESTIMATED COMPLETION OF DESIGN:  November 2019

ESTIMATED COMPLETION OF CONSTRUCTION: May 2020

CONSTRUCTION COST:  To Be Determined

CONTRACTOR: To Be Determined

Borough Council authorized the engineering services at their May 14, 2019 Council Meeting. Asphalt cores were taken along East Central Avenue. Survey has been completed. Existing condition base plans have been prepared. Final construction plans and specifications are complete. Plans, Specifications, Design Certification and Estimate have been sent to the NJDOT Local Aid for review and approval prior to public advertisement for construction bids. NJDOT approved the construction documents and the project is advertised for public construction bids. Bids will be received on February 20, 2020 with the anticipation of a contract award at the February 25, 2020 Council Meeting.

- STaTe Route 122 and InduStrial Drive Intersection ImprovemEnts (NJDOT LOcal Aid Freight GRant)

ESTIMATED COMPLETION OF DESIGN:  February 2020

ESTIMATED COMPLETION OF CONSTRUCTION: August 2020

CONSTRUCTION COST:  To Be Determined

CONTRACTOR: To Be Determined

Borough Council authorized the engineering services at their November 26, 2019 Council Meeting. The left turn traffic analysis is in progress. Survey is completed and base plans are being prepared.

- Reconstruction of 5th Avenue – Phase III (NJDOT LOcal Aid FY 2020 Grant)

ESTIMATED COMPLETION OF DESIGN:  March 2020

ESTIMATED COMPLETION OF CONSTRUCTION: July 2020

CONSTRUCTION COST:  To Be Determined

CONTRACTOR: To Be Determined

Borough Council authorized the engineering services at their January 14, 2020 Council Meeting. Survey and base plans are completed. Preliminary design is in progress.

- Industrial Road Extension

ESTIMATED COMPLETION OF DESIGN:  November 2019

ESTIMATED COMPLETION OF CONSTRUCTION: May 2020

CONSTRUCTION COST:  To Be Determined

CONTRACTOR: To Be Determined

Borough Council authorized the engineering services at their November 26, 2019 Council Meeting. Proposed roadway baseline is complete and field survey is complete. Base plans are being prepared.

- NJPDES PERMIT – INDUSTRIAL DRIVE LANDFILL DISRUPTION PERMIT

ESTIMATED COMPLETION OF DESIGN: January 2020

ESTIMATED COMPLETION OF CONSTRUCTION: NA

ESTIMATED CONSTRUCTION COST:  NA

CONTRACTOR: NA

The next phase of the work has been authorized and initiated.   A status meeting will be scheduled for early November to review progress and initial results.  Field work is complete and we are awaiting laboratory results.  Final report was submitted to NJDEP on January 15, 2020.  We are awaiting any comments from NJDEP.

- NJPDES PERMIT – INDUSTRIAL DRIVE MAJOR LANDFILL DISRUPTION PERMIT

ESTIMATED COMPLETION OF DESIGN: February 2020

ESTIMATED COMPLETION OF CONSTRUCTION: NA

ESTIMATED CONSTRUCTION COST:  NA

CONTRACTOR: NA

This phase of the work has been authorized in December 2019 and initiated.   It is anticipated that a draft will be available for review at the end of February 2020.

WATER   PROJECTS

.

- 2018 WATER UTILITY IMPROVEMENTS

ESTIMATED COMPLETION OF DESIGN:  March 2, 2018

ESTIMATED COMPLETION OF CONSTRUCTION: September 2018

ESTIMATED CONSTRUCTION COST:  TBD

CONTRACTOR: TBD

The County has issued the permit.   The work had to be postponed due to the County schedule.   A meeting was held October 16th to review the schedule with the contractor and the County.  The County restoration was scheduled for the following week.  Final connections are to be arranged with homeowners.

- ASSET MANAGEMENT PLAN (AMP)

ESTIMATED COMPLETION OF DESIGN:  Final Review – May 2019

ESTIMATED COMPLETION OF CONSTRUCTION: NA

ESTIMATED CONSTRUCTION COST:  NA

CONTRACTOR: NA

The AMP is complete.    A draft report will be provided this week for review with the Borough at the October 16th meeting.  A draft report has been submitted to the Borough.

ASSET MANAGEMENT PLAN (GIS)

ESTIMATED COMPLETION OF DESIGN:  Two weeks after receipt of Borough Comments

A review meeting was held on 12/13/2019 and follow-up conference call on 2/5/2020 with the Borough to review draft water system maps. These review maps included for reference were as follows:

-Edge Road connector Pdf (latest information given to us/Added to the map)

-Water Utility mark-up that displays any areas that are unverified/areas we have as-built information as well as previously surveyed information

-Water utilities overall map

-Water utilities over map with aerial turned on

The DPW is to review these documents and confirm the water assets found. We will use this to identify and target any missing/obscured areas that need to field verified and collected.

- FRACE WTP O&M MANUAL

ESTIMATED COMPLETION OF DESIGN:  January 2020

The development of the Frace WTP O&M Manual has been authorized.    We are currently preparing the outline and will be meeting with the Borough and Operator to develop sequencing scenarios in Early February.  Submission for Borough review is anticipated by March 2020.

- NJDEP Water System Inspection.

An Inspection by NJDEP was conducted on January 7, 2020.  Initial comments from NJDEP were positive with no deficiencies noted.  We are awaiting the formal results from the inspection.

SANITARY   PROJECTS

- SANITARY METER VAULT INSTALLATION

ESTIMATED COMPLETION OF DESIGN:  July 2018

ESTIMATED COMPLETION OF CONSTRUCTION: 30 Days upon issuing Notice to Proceed

ESTIMATED CONSTRUCTION COST:  $40,000

CONTRACTOR: TBD

Bid Documents are being prepared for installation of the meter vault since the requested quotes were higher than the bid threshold.  The results of the second bid received January 7, 20102 was one bidder submitted a bid.  This exceeded the Engineering estimate and RVE would recommend rejection of the bid and negotiation of bids consistent with the Local Public Contracts Law. Council authorized negotiations with Contractors.

MISCELLANEOUS PROJECTS

- lEIGH fUEL pROPERTY INVESTIGATION

The Leigh Fuel property preliminary assessment (PA) was authorized by Council at the November 28, 2018 meeting and the grant documents have been executed. A site visit was conducted and we performed a desk top survey of the property. The PA is complete and has been submitted to the NJDEP. A proposal had been provided to Council for their consideration of advancing the assessment through additional grant dollars.  The Grant Application has been submitted to the NJDEP.

2.	GIS ROSI Map Updates with Flood prone Area Overlay for the Borough of Alpha, County of Warren, New Jersey

The ROSI Map updates with flood prone areas calculated and overlaid onto the GIS map layer was authorized on 11/26/2019 under resolution #2019-164. We have completed the updated ROSI map for Alpha Borough applying the additional areas and the 100-year flood prone areas with acreages documented. A DRAFT map was provided on 12/30/2019 as a PDF file for review along with the Green Acres List for reference.  A follow-up conference call was held on 2/5/2020 to address additional questions.  Once any edits are applied and approved, we will prepare the final deliverable at the Borough’s direction per our 11/15/2019 proposal.

- Tax Map Maintenance/Revisions for the Borough of Alpha for Tax Year 2020

The 2020 Tax Map Maintenance proposal was submitted and approved by the Borough per resolution 2020-41, dated 1/14/2020 per our proposal dated 11/15/2019.  This work will be performed over the course of the year and will be filed with County Tax Board No Later Than January 2021.

- Census Map Maintenance/Revisions for the Borough of Alpha for Tax Year 2020

(To be filed with Census Bureau by March 1, 2020)

A review conference call was held on 2/5/2020 with the Mayor to review Borough tax map municipal boundary changes that may have occurred since the last 2010 census included, but not limited to, any annexations, boundary inaccuracies and similar adjustments as well as the addition of any new development to the tax Borough.  RVE is already authorized to update and submit this mapping to the Census Bureau and will review and address any discrepancies once the paperwork has been received from the Borough as directed. This work needs to be completed and delivered to the Census Bureau by 3/1/2020.