## Sheet1
Township of Edison
Water Department
5-Year Capital Improvement Plan 2020-2024
Improvement | Project Description | Estimated Eng Design Cost | Estimated Construction Phase Engineering | Estimated Other Project Costs (1) | Estimated Project Cost | 2020 Expenditure | 2021 Expenditure | 2022 Expenditure | 2023 Expenditure | 2024 Expenditure
Water Meters | Replacement of All Water Meters with Smart Meters and New Reading System | 340000 | 300000 | 275000 | 7100000 | 2600000 | 4500000
Water Mains (min.) | Replace or Rehabilitate approx. 6,000 ft of pipe per year to comply with WQAA (Min. 0.8% replacement rate) | 0 | 40000 | 0 | Annual | 1200000 | 900000 | 900000 | 900000 | 900000
Water Mains & Accessories | Replace or Rehabilitate Additional Water Main, Replace Inoperable Valves, Replace Hydrants | 200000 | 225000 | 200000 | Annual | 1100000 | 1400000 | 1470000 | 1477000 | 1482000
Facility | Develop/Construct/Install SCADA System, Install Systems at Water Purchase Interconnections | 35000 | 30000 | 10000 | 260000 | 260000 | 0 | 0 | 0 | 0
| Total | 575000 | 595000 | 485000 |  | 5160000 | 6800000 | 2370000 | 2377000 | 2382000
| Total 2020-2024 Expenditure |  |  |  | 19089000
Last updated 5/31/2020